## Sprint 1 Backlog
Sprint Name: | Sprint 1 – MVP Development
Sprint Duration: | 2 Weeks
Sprint Goal: | Deliver the basic Smart-Attend app with login, geo-fencing attendance detection, and notifications.
Task ID | User Story (As a..., I want..., So that...) | Priority | Estimated Hours | Assigned To | Status
US01 | As a student, I want to login via university ID so I can access my profile. | High | 4 | Backend Dev | To Do
US02 | As a teacher, I want to view a real-time list of present students. | High | 6 | Frontend Dev | To Do
US03 | As a system, I want to detect if a student is within 10m of the classroom. | High | 8 | Backend Dev | To Do
US04 | As a student, I want a notification when my attendance is marked. | Medium | 3 | Mobile Dev | To Do
US05 | As an admin, I want to manually override attendance for technical errors. | Low | 4 | Backend Dev | To Do